Task 3: Resource Allocation and Capacity Planning

Project: Marketing Website Update

Date: 12/20/2025

1. Introduction

Resource Allocation and Capacity Planning ensure that the right resources are assigned to project tasks, and that team capacity is sufficient to complete the work within the project timeline. This section maps project activities to specific roles including developers, QA engineers, DevOps engineers, and designers. It also evaluates resource utilization, identifies potential skill gaps, and highlights risks that may impact project delivery.

| Task | Resource | Role |
| --- | --- | --- |
| Project Kickoff | Project Manager | PM |
| Website Analytics Review | UX / SEO Specialist | Analyst |
| Wireframes & User Flows | UX Designer | Designer |
| Visual Design | UI Designer | Designer |
| CMS Setup | Backend Developer | Developer |
| Front-end Development | Front-end Developer | Developer |
| Technical SEO | SEO Specialist | SEO |
| Deployment | DevOps Engineer | DevOps |
| Functional Testing | QA Engineer | QA |
| Content Migration | Content Team | Content |

2.    Capacity & Utilization Report

| Role | Estimated Total Effort | Team Capacity | Utilization |
| --- | --- | --- | --- |
| Project Manager | ~18 days | 40 days available | 45% |
| UX Designer | ~17 days | 30 days available | 57% |
| UI Designer | ~20 days | 30 days available | 67% |
| Front-End Developer | ~27 days | 40 days available | 67% |
| Backend Developer | ~17 days | 30 days available | 57% |
| DevOps Engineer | ~8 days | 20 days available | 40% |
| QA Engineer | ~18 days | 30 days available | 60% |
| SEO Specialist | ~12 days | 25 days available | 48% |
| Content Team | ~11 days | 20 days available | 55% |
| Analytics Specialist | ~5 days | 15 days available | 33% |

Key Observations

Front-end and UI resources have the highest workload concentration during development.

DevOps capacity is sufficient since involvement occurs mainly during deployment and optimization.

QA workload increases significantly during the testing phase, requiring careful scheduling.

3.  Skill Gap Analysis

| Area | Gap | Impact | Mitigation |
| --- | --- | --- | --- |
| Accessibility (WCAG 2.1 AA) | Limited internal expertise | Risk of compliance issues | Accessibility consultant review |
| Advanced SEO implementation | Technical SEO complexity | Reduced organic performance | SEO specialist support |
| Performance optimization | High-speed performance targets | Risk of missing <2.5s load target | DevOps tuning and CDN |
| CMS modular architecture | Team may lack experience with headless CMS | Development delays | Provide CMS training |

4.  Resource Risks

| Risk | Impact | Mitigation |
| --- | --- | --- |
| UX/UI design delays | Development schedule impact | Early design review cycles |
| Front-end resource overload | Slower development pace | Add backup developer |
| Content migration delays | Launch timeline risk | Begin migration early |
| QA resource shortage | Bugs at launch | Parallel QA testing |

5.   Recommendations

- Assign dedicated front-end developers during the development phase.

- Conduct early accessibility and SEO reviews to reduce rework.

- Introduce weekly capacity reviews during development and QA phases.

- Maintain backup resources for critical roles (Front-End Dev, QA).

Deliverables Completed

- Resource Allocation Matrix

- Capacity & Utilization Report

- Skill Gap Analysis

- Resource Risk Assessment